## 2
Strategic Risk Register
2 |  |  |  | External legislative changes affect the status of the Union or the financial benefits utilised by our activities.
Residual Status |  |  |  | AMBER | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Impact |  |  |  | External legislative changes affect the status of the Union or the financial benefits utilised by our activities. AMBER: • Loss of charitable status • Requirement to register commercial activities with a subsidiary company liable for corporation tax
Executive Lead |  |  |  | External legislative changes affect the status of the Union or the financial benefits utilised by our activities. AMBER: Head of Finance & Resources
Score |  |  | Control in place | External legislative changes affect the status of the Union or the financial benefits utilised by our activities. Jan: Pending Controls
Impact | Likelihood | Effectiveness of Controls
High | Medium |  |  | External legislative changes affect the status of the Union or the financial benefits utilised by our activities. AMBER: • Financial stability through reserves; External legislative changes affect the status of the Union or the financial benefits utilised by our activities. Feb: * SMG responsible for staying up to date with Sector changes
• Political networking
• Collaboration with College
• Knowledge of students’ unions legal status
• External Audit recommendations have been received
Comments / Updates: |  | * Paused engagement of external consultant to drive review of commercial activity triggers that might make it neccesary for a separate Limited trading company.

## 6
Strategic Risk Register
6 |  |  |  | Social Enterprise operations suffer significant downturn, fraud or loss of license leading to financial deficits.
Residual Status |  |  |  | AMBER | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Impact |  |  |  | Social Enterprise operations suffer significant downturn, fraud or loss of license leading to financial deficits. AMBER: • Losses in revenues impacting on ability to delivery key services • Job losses for our membership • Social space loss • Negative affect on College relationship • Impact on local neighbourhood relationships
Executive Lead |  |  |  | Social Enterprise operations suffer significant downturn, fraud or loss of license leading to financial deficits. AMBER: Head of Commercial Services
Score |  |  | Control in place | Social Enterprise operations suffer significant downturn, fraud or loss of license leading to financial deficits. Jan: Pending Controls
Impact | Likelihood | Effectiveness of Controls
|  |  |  | • Clear, robust operating and financial procedures regularly tested and Audited | [5 empty] | *Implementation of all Internal Audit recommendations
High | Low |  |  | Social Enterprise operations suffer significant downturn, fraud or loss of license leading to financial deficits. AMBER: • Timely and accurate financial information and reporting
* Structural change to create a Commercial Services Directorate and therefore increased capacity for strategic developments#
• Regular review of product mix to ensure it caters to wants and needs of all members
Comments / Updates: |  | New Operations Manager joined in March 2019 to support the structural changes on Commerical Services

## 8
Strategic Risk Register
8 |  |  |  | Failure to implement an effective people management strategy leading to ongoing staffing challenges and weakening external standards.
Residual Status |  |  |  | AMBER | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Impact |  |  |  | Failure to implement an effective people management strategy leading to ongoing staffing challenges and weakening external standards. AMBER: • Failure to recruit and retain great staff members • Loss of institutional memory • Loss of a supportive community in staff team • Low staff morale or effectiveness • Failure to follow employment regulations and laws
Executive Lead |  |  |  | Failure to implement an effective people management strategy leading to ongoing staffing challenges and weakening external standards. AMBER: Managing Director and Head of Finance & Resources
Score |  |  | Control in place | Failure to implement an effective people management strategy leading to ongoing staffing challenges and weakening external standards. Jan: Pending Controls
Impact | Likelihood | Effectiveness of Controls
|  |  |  | • Strong links with College HR and knowledge of their processes | [5 empty] | * Succession & Contingency planning working group
Medium | Medium |  |  | Failure to implement an effective people management strategy leading to ongoing staffing challenges and weakening external standards. AMBER: * Significant Training and Development budget with focus on key areas for Union-wide development / growth supported through Access-to-training scheme
* Achieved Gold status for Investors in People
*Internal Comms group not established, however Leadership has taken owership of intenal comms with oversight from Comms Committee
* Clear standards for one-to-ones, team meetings, Personal Development Reviews (PDRs) and Union Our Standards
Comments / Updates:

## 9
Strategic Risk Register
9 |  |  |  | A significant failure to our IT systems resulting in services being unavailable or commercial activity affected.
Residual Status |  |  |  | RED | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July
Impact |  |  |  | A significant failure to our IT systems resulting in services being unavailable or commercial activity affected. RED: • Significant functionality loss across whole organisation • Productivity loss • Regulation issues surrounding the breach of data safety • Risk to audit rating • Reduction in club functionality and autonomy • Significant data breach and loss of personal data
Executive Lead |  |  |  | A significant failure to our IT systems resulting in services being unavailable or commercial activity affected. RED: Head of Finance & Resources
Score |  |  | Control in place | A significant failure to our IT systems resulting in services being unavailable or commercial activity affected. Jan: Pending Controls
Impact | Likelihood | Effectiveness of Controls
|  |  |  | • All essential services are hosted on virtual servers | [5 empty] | * Regular stress testing of systems
High | Medium |  |  | A significant failure to our IT systems resulting in services being unavailable or commercial activity affected. RED: • Clear management responsibilities; A significant failure to our IT systems resulting in services being unavailable or commercial activity affected. Feb: * GDPR compliance monitoring
|  |  |  | • Staff support for key systems with back up documentation and shared knowledge | [5 empty] | * Succession planning for systems roles with significant institutional knowledge
Comments / Updates: |  | Key risk areas of individual knowledge / ability identified (especially Elections processes) and mitigating plans being worked through.

## Key
Scoring Key | Levels
| 1 | 2 | 3
Risk Status | GREEN | AMBER | RED
& | Adequate | Concern | Alarm
Effectiveness of Controls
| SMG Lead | No of Risk
| Jarlath | 1, 3, 7, 10, 11
| Malcolm | 2, 7, 9
| Andrew | 4, 5, 10
| Julia | 6
| Paul | 10, 11