## Pipeline
Summary: Draft 19/20 Systems Pipeline
|  |  | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01
Business as usual
| Customer Support |  | 2019-09-01: Heavier
CSP server support (cover for Sys Adm) | bar: 2019-07-01 to 2019-10-01
Staff Support queries (e.g. Imperial Award, Website Beit) | bar: 2019-07-01 to 2019-10-01
EPOS / till support / improvements
Data Protection support / training
Graduation | bar: 2019-10-01; 2020-05-01
| Elections |  | 2019-07-01: Planning
Year End - CSP, Halls, Sports Committee structure | bar: 2019-07-01 to 2019-08-01
Welcome Hub (15 August) | bar: 2019-08-01
Website Face lift | bar: 2019-07-01 to 2019-09-01
Projects
1 | Drupal 8 configuration | Phil | bar: 2019-06-01 to 2019-08-01
2 | Online Shop & CSP products (joint) | Phil | bar: 2019-06-01 to 2019-08-01
3 | Mini Bus | bar: 2019-06-01 to 2019-08-01
4 | Summer Ball - Front Gate | bar: 2019-06-01
Potential Projects
5 | E -Voting Platform | 12 month project…- targeting Autumn 2020
6 | Website Redevelopment | 1 -2 month project
7 | Sport Clubs - eActivities access - authorisations |  | 2019-08-01: minor
8 | EPOS
9 | Petitions / Campaigns Module - brief needed?
10 | Imperial Award | bar: 2019-08-01 to 2019-09-01
11 | Work Shop / Registration / Attendance | bar: 2019-08-01 to 2019-09-01
12 | Events Procedure
13 | Events Risk Assessments
|  |  | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01
CSP Server migration
Notes:
Website front page landing - frame layout changes
Home page review
Beit Venue - website - some minor development

## Context
| Draft: Project Context | Deadline | Risks
1 | Drupal 8 upgrade | 2019-08-31
| Foundation piece |  | Co-dependent with Online Shop project - cannot go live until both are complete
Rebuild existing Drupal 7 functionality in Drupal 8 (e.g. CSPs, Rep Centres, What's On)
Rebuild site theme using Foundation 6
Re-implement & improve basic site structure and navigation
Improved content authoring & migration of existing content
New user account processes with on-demand migration from Drupal 7 accounts
Site configuration and deployment workflow
Fallback mechanism to Drupal 7 site for content / functionality not implemented before go-live
2 | Online Shop & CSP products (joint) | 2019-08-31
| The web-based online Shop is also used by CSP's to host their "products". The new shop will be a migration from that hosted on Drupal 7 |  | Co-dependent with Drupal 8 Upgrade project - cannot go live until both are complete
New shop theme designed with the Shop brand
Core shop functionality: products & taxonomy
New API for creation of CSP products and rebuild of eActivities -> Dotorg product transfers
Payment gateway
Order placement and record keeping (data transfer to eActivities & Finance)
Retail order fulfillment workflow and shipping
4 | Summer Ball - Front Gate | 2019-06-01
Essential piece to manage guest customer data: tickets transfers and external guest registration
8 | EPOS |  | RISK
8 | 1. Installation in H Bar to aid control & additional info 2. New store licenses for H Bar & Metric 3. Potential of additional hardware = 1 * new till |  | No resource to support this
5 | E -Voting Platform |  | RISK
5 | Build new voting system from scratch, improvements to admin functions, calculations and outputs and writing to modern standards. 1. Nominations platform 2. Voting module 3. Returning Officer module (Candidate & Complaints management, results processing) 4. Administration module (position setup and electoral roll population) |  | Modular, big project - probably start autumn 19
6 | Website Redevelopment |  | RISKS
6 | Beit Venues site redevelopment - needs to be done on Drupal 8 |  | Duplication of work if started before drupal 8 upgrade completed
9 | Petitions / Campaigns Module |  | RISKS
9 | scope has already given by SVC - Campaign ideas - capture support - then trigger a campaign |  | Duplication of work if implemented in Drupal 7 before completion of Drupal 8 upgrade
counting & signature sign-up
10 | Imperial Award
Registration process changes for Business Scholl and PGR students
Submissions eligibility - students should only be able to submit if enrolled for duration of submissions period
11 | Leadership Development Program (modular pieces)
Registrations / attendenace -- has a general purpose for all training workshops (SA, E&W, and SD)
training quizes
record keeping
workshop functionality
12 | Events procedure
Holistic approach to CSP event organisation incorporating unified record keeping for all resources required by an event (e.g. rooms, external speakers, risk assessment, etc)
13 | Events Risk Assessments
Basic implementation to plug record-keeping gap until full implementation in 'Event procedure' project

## Key
Project Key:
Risk Indicator
Project is on time
Project at risk of slippage
Off track / no resources