## Strategy Plan
Planks | Main Objectives | Actions | Projects | Year 1 | Year 2 | Staff Lead | Support roles
|  | Clarify our value proposition | Brand Refresh Project Part 1 | Ongoing; Complete by December |  | HoSVC | Marcomms Manager; Senior Designer
|  | Develop a content strategy that communicates these simply and clearly to members, Union staff and College partners | Prepare shareable Content Plan | November |  | Marketing Manager | Marcomms Coordinators
Communicating Value | Awareness; Ease of Engagement | Restructure our content and channels around our value proposition to members | Web Refresh (Navigation, Homepages, landing pages) ; Social media strategy | ongoing; Complete by December |  | HoSVC | Senior Designer, Marcomms Coords
We will be clear about who we are and communicate our value to members and partners |  | Include About section in main navigation and redevelop section
|  | Create a Union boilerplate that captures who we are and is consistently applied across all our spaces and channels | Brand Refresh Project Part 1 | Ongoing; complete by December |  | HoSVC | Marcomms Team
|  | Update our brand to ensure that all our programmes are visually and thematically subordinate to the Union brand | Brand Refresh Part 2 | Complete end of May 2020 |  | Senior Designer | Marcomms Team
|  | Create termly comms plans for problem areas such as Commercial areas and PGs | Tactical Comms Plans for PGs and Commercial | By November Comms Committee |  | Marcomms Manager
|  | Redevelop our website | Web Redevelopment | Scope and content review by January 2020 | Complete by December 2021 | HoSVC | Marcomms and Systems
|  | Digitise external processes | Identify processes within BAU and major projects | scoping and solutions ongoing | scoping and solutions ongoing | HoSVC | Junior Web developer. Efficiency project
|  | Provide physical access to Union computer/software and training to volunteers with comms roles | Rep Structures Support Review Project | Term 1 | review | Representation Manager | Marcomms Manager; Senior Designer
Channels and Competencies | Ease of Engagment; Professionalism | Complete skills audit and start skills exchange programme for comms team | Marcomms Lunch and Learn Programme | ongoing, starts term 1 | ongoing | Marcomms Manager | Marcomms Team
We will improve our digital and physical spaces, as well as our people competencies to deliver both ease of engagement and excellent communications |  | Create templates for each area of delivery that facilitates more efficient communications | Brand Refresh part 2 | start with social enterprise in term 1 | complete every area by start of term | Senior Deisgner | Marcomms coordinator
|  | Develop our spaces according to our brand and ensure the proper channels are in place in the right locations. | Space Refresh | TBD | TBD | TBD | TBD
|  | Develop a programme for engagment using: social incentive, progress monitoring and immediate rewards | Strategic Engagement | Scope | Implement before term 1 | HoSVC | Systems, Marcomms Team and all managers
|  | Create signature for emails | Brand Refresh Part 1 | by January 2020 | review and update | Senior Designer | Systems
|  | Complete comprehensive Marketing Calendar | BAU | Ongoing as the year develops | update | Marcomms Manager | all staff
|  | Implement a student ambassadorship programme where influencers can be identified in each faculty to help disseminate information (hiring scheme or through the election of a Communications Rep) | subject to approval | subject to approval |  | HoSVC | Systems , HoSE
|  | Create a social media strategy that give CSPs, Senior Reps, and members ownership of channels through regular takeovers | Update social media strategy | term 1 | update | Marcomms coordinators | Rep team, Activities team
|  | Allow students direct access to the web’s What’s On pages to promote their events and activities | Rep Structures Support Review Project | term 1 | review | Systems Manager | Events Coordintaor, Activities & rep managers
Information to Conversation | Ownership; Awareness; Belonging | Promote student events on main social media pages | Social Media Strategy and Content Strategy |  |  | Marcomms Manager | Marcomms Coordinators
We will move from a model of talking at our members towards facilitating conversations with and among members. |  | Feature members’ stories and testimonials in Union communications such as reports and social media | Content Plan | November; ongoing |  | Marcomms Manager | Marcomms Team
Incorporate celebration days with members through the development of
|  | Facilitate consultations on development of Union Strategy | Union Strategy Development | ongoing |  | HoSVC | Marcomms Team, Ots
|  | Host regular briefings with Senior Reps | Rep Structures Support Review Project | Termly; ongoing | ongoing | Rep Manager | HoSVC; Relevant Managers
Powering our Democracy | Ownership; Awareness; Professionalism | Host OTs on tour | OT Comms Plan | Term 1; ongoing | review | President | OTS, Marcomms team
We will drive our democracy through structured consultations and further devolution of communications |  | Write comms plans for OTs, Union Council, CUs, and Liberation Officers | Rep Structures Support Review Project | Term 1; ongoing |  | Rep Manager, Gov Coordinator | Rep Coordnators, Marcomms Manager, OTs
|  | Implement Union townhalls | OT Comms Plan | as required | as required | President | HoSVC, Leadership, Marcomms Team, all staff

## Structure of Marketing
Tasks | Marketing & Communications Manager | Senior Designer | Marketing & Communications Coordinator | Sales & Sponsorship Manager
OVERALL DESIGN WORK | Messaging lead on all projects e.g. ideas, briefs, copywriting, implementation | Design lead on big projects, e.g. Elections, Summer Ball, Welcome Week - ideas, briefs, implementation | Design assistance on big projects e.g. Elections, Summer Ball, Welcome Week, focusing on social media/digital content
FINANCE/SALES | Finance responsibility for team - budget holder, working with team to set income and expenditure, implementation and oversight of budget income, expenditure and procedures. Performing month end procedure. | Contributing to and adhering to assigned expenditure targets. Perform admin processes, e.g. POs, transfers, credit card requests | Contributing to and adhering to assigned expenditure targets. Perform admin processes, e.g. POs, transfers, credit card requests | Work with M&C Manager to set income targets. Responsible for achieving income targets set, and adhering to necessary expediture targets. Perform admin processes, e.g. invoicing, POs, transfers, credit card requests. Also performing month end procedure.
SOCIAL MEDIA | Oversight of day-to-day and project social media. Assist with social media updates or content if need be. | Support M&C Coordinators with design visuals for social media. | Day-to-day and project social media content, plans and implementation. Create and coordinate project social media plans sign off from M&C Manager and/or Head of SVC. Liaise with relevants teams on content. | Liaising with M&C Manager and M&C Coordinator (commercial) in regards to social media sales, handing over relevent information for scheduling and posting.
WEBSITE | Monitoring and editing Union and sub websites (e.g. Beit Venues, Elections, Summer Ball) with team. Design work and training for website where required. | Design and implementation work for website and visual content, e.g. new Union design, sub sections. | Monitoring and editing generic website sections (e.g. homepage, news, About Us). Work on sub sites where needed also. Regularly reviewing other sections and updating with/for necessary teams | Monitoring and editing following website sections: ads on website, student discounts section, Advertise with Us section
SCREENS | Managing admin of screens, e.g. agreements, maintenance | Creating content for digital screens as required | Assist with admin of screens, e.g. agreements, maintenance. Creating, uploading and scheduling content (all screens). | Liaising with M&C Manager and M&C Coordinator (commercial) in regards to screen sales, handing over relevent information from external clients. Managing screen agreements alongside the M&C Manager.
WALKWAY | Oversight of poster spaces and messaging. | Arranging, sourcing and/or designing posters for Sherfield walkway. | Arranging, sourcing and/or designing posters for Sherfield walkway. Putting posters up on display, ensuring walkway is up to date. | Liaising with M&C Coordinator (commercial) in regards to poster space sales, handing over relevent information from external clients.
CENTRAL UNION COMMS | Responsible for ensuring consistency in central Union comms, e.g. responses, reports, forms, signage. Design and/or copy work where need be. | Responsible for ensuring consistency in central Union comms, e.g. responses, reports, forms, signage. Design and/or copy work. | Responsible for ensuring consistency in central Union comms, e.g. website, social media. Design and/or copy work. | Ensuring comms to external clients is consistent with Union brand.
LICENSED TRADE | Working with Commercial Team to field monthly requests and long term projects. Produce any necessary marketing plans. | Working with Licensed Trade team to field monthly requests and long term projects. Materials and resources for monthly requests and/or long term projects as directed. | Work with M&C Manager to coordinate and execute necessary marketing plans. Produce vouchers for events where necessary. | Work with M&C Manager and Commercial Team on sales/sponsorship opportunities within their department.
COMMS FOR DEPARTMENTS/TEAMS e.g. Student Development, Student Activities, Officer Trustees | Work with teams on their requests for comms, e.g. ideas, briefs, scheduling, advice, sign off on plans | Work with teams on their requests for comms, e.g. ideas, briefs, scheduling, advice | Work with teams on their requests for social media communication. Materials and resources for requests and/or long term projects as directed | Work with M&C Manager and teams on sales/sponsorship opportunities within their department
NEWSLETTER | Main administrator for Union MailChimp account. Lead on messaging/content inclusion for newsletters. | Support M&C Coordinators with design visuals for newsletter where required. | Secondary admin for Union MailChimp account. Creation of central newsletter and one-off newsletters. Analyse and report on data from MailChimp to help improve emails sent. | Sourcing adverts for newsletters and scheduling in with Manager and Designer. Handing over any relevant information from external clients.
FAIRS | Oversight of income, expenditure and organisation for fairs. Development of events year on year. Manage promotion of fairs to students. Help at fair events on the day. | Produce materials needed for fairs, e.g. brochures, maps, posters. Help at fair events on the day. | Assist with producing materials needed for fairs, e.g. brochures, maps, posters where applicable. Assist with promotion of fairs to students. Help at fair events on the day. | Responsible for income, expenditure and organisation for fairs. In particular, work on Welcome' Fair with M&C Manager and Events team. Development of events year on year. Manage promotion of fairs to students. Manage fair events on the day.
OFFICER TRUSTEE AND SABB COMMS | Manage production of materials for the start of new OT and Sabb tenure (August) - website updates, graphics for screens, posters for building and walkway, business cards, clothing. | Production of materials for the start of new OT and Sabb tenure (August). | Support with production of materials for the start of new OT and Sabb tenure (August) and introduction of new OTs and Sabbs to students via social media.
WELCOME WEEK | Manage production of Union materials for Welcome Week, working with teams on their requests and requirements. Manage production of Welcome video. Manage production of materials. | Production of materials for Welcome Week, working with M&C Manager and teams on their requests. Support production of Welcome video. | Coordination of materials for Welcome Week, working with M&C Manager and teams on their requests. Manage Union Welcome Week digital presence (website, social media). Work on production of Welcome video.
FELIX | Work with Sales & Sponsorship Manager on income and expenditure for adverts and printing. Maintain relationship with Felix Editor. | Produce Union page, Ents page and/or adverts for paper to deadline for each issue. | Produce content for Union page for paper to deadline for each issue, work with Senior Designer and S&S Manager on content and/or adverts. | Responsible for income, expenditure and admin for adverts and printing. Maintain relationship with Felix Editor.